## Dashboard
Test Summary & Quality Gate Report
Project Name: | OpenCart E-Commerce Platform
Testing Cycle: | V1.0 - Manual Execution Phase
Execution Date: | June 2026
QA Lead: | Abdullrahman Emad
Test Execution Metrics |  |  |  | Defect Classification (Severity)
Metric | Value | Percentage |  | Severity | Count | Priority Allocation
Total Test Cases Designed | 207 | - |  | Critical / Blocker | 3 | 2 High, 1 Medium
Total Test Cases Executed | 207 | 100.0% |  | Major | 6 | 6 Medium
Passed Test Cases | 187 | 90.3% |  | Minor | 11 | 3 Medium, 8 Low
Failed Test Cases | 20 | 9.7% |  | Total Logged Defects | 20 | 20 Total
QUALITY GATE STATUS: PASSED WITH RESERVATIONS
Module-Wise Testing Distribution
Module / Feature | Test Cases | Passed | Failed | Bugs Found | Status
User Registration | 19 | 17 | 2 | 2 | Fix Verified
User Authentication (Login/Logout) | 27 | 27 | 0 | 0 | Stable
Product Search & Navigation | 20 | 19 | 1 | 1 | Minor Issue
Currencies Management | 3 | 3 | 0 | 0 | Stable
Product Display & Comparison | 58 | 56 | 2 | 2 | Minor Issue
Shopping Cart Management | 9 | 8 | 1 | 1 | Fix Verified
Checkout & Order Finalization | 20 | 19 | 1 | 1 | Fix Verified
My Account Profile | 9 | 9 | 0 | 0 | Stable
Newsletter Subscription | 13 | 13 | 0 | 0 | Stable
Contact Us Validation | 13 | 13 | 0 | 0 | Stable
Others / UI Adjustments | 16 | 3 | 13 | 13 | Under Review